## Controlling Script
Subsection | Module Name | Developed | Tested (2008R2-2016) | Known Issues | Proposed Modifications
YACK.ps1 | Start-RemoteCollection | TRUE | FALSE -Haven't tested Kerb Auth |  | *-Create a collection summary that enough information that you dont need to dig into logs. -Figure out how to use something other than psremote? Probably not
| Test-Settings | TRUE | FALSE |  | -Validate output path
| Invoke-WinRM | FALSE |  |  | Invoke-StartWinRm https://github.com/mgreen27/Powershell-IR/blob/master/Invoke-LiveResponse.psm1
| Invoke-StopWinRM | FALSE |  |  | Invoke-StopWinRm https://github.com/mgreen27/Powershell-IR/blob/master/Invoke-LiveResponse.psm1
Collectors.ps1 | Write-CollectorResult |  |  |  | Add Support for ChunkCSV
DataTransfer.ps1 | YACKPipe-ReturnFile | Partial |  | YACKOutputFolder as $null does not default to collector folder name

## Collectors
Subsection | Module Name | Developed | Tested (2008R2-2016) | Known Issues | Proposed Modifications | Info
Apps
| Get-HBSS-Events | TRUE | Partial (2.0) | test with live hbss | Incorporate backup event logs... .01 .02 | Parses the simple HBSS event logs
| Get-HBSS-HIPShield | TRUE | Partial (2.0) | test with live hbss | Incorporate backup event logs... .01 .02 | Parse the detailed HBSS event log
| Get-IIS-DirListing | TRUE | Partial (2.0) |  |  | Reads the registry key entry for ISS and does a dir listing for the folder
| Get-IIS-WebsitesInfo | TRUE | Partial (2.0) |  | Expand bindings into a json object | Parse out the websites that are hosted on this server
| Get-IIS-AccessLogs | FALSE - Here |  |  | Files will need to be chunked back | Parse the Access Logs
| Get-IIS-ErrorLogs | FALSE |  |  |  | Parse the Error Logs
| Get-FirewallLogs | FALSE
| Get-OfficeRecentFiles | FALSE |  |  |  | SANS Windows DFIR Poster MS Office programs will track their own Recent Files list to make it easier for users to remember the last file they were editing.
| Get-OutlookAttachments | FALSE |  |  |  | SANS Windows DFIR Poster
| Get-IEFileInteractions | FALSE |  |  |  | SANS Windows DFIR Poster
| (?) Get-BrowserCache | FALSE
| Get-BrowserArtifacts | FALSE |  |  |  | SANS Windows DFIR Poster
| Get-BrowserDownloadHistory | FALSE |  |  |  | SANS Windows DFIR Poster
| Get-BrowserCookies | FALSE
| Get-BrowserHistory | FALSE
| Get-SkypeHistory | FALSE |  |  |  | SANS Windows DFIR Poster
Exec_Current
| Get-Processes | TRUE | Partial (2.0) | Get owners has no exeception catch on finding the parent. | -It's slow. Use hash table lookups instead.
| Get-ProcessHandles | TRUE | Partial (2.0)
| Get-ProcessModules | TRUE | Partial (2.0)
| Get-ProcessSockets | TRUE | Partial (2.0)
| Get-Services | TRUE | Partial (2.0) |  | -Relies on autorunsc.exe | Can pull drivers from the 2 registry keys. (Just import from autoruns powershell github)
| Get-Drivers | TRUE | Partial (2.0) |  | -Relies on autorunsc.exe. | -Can pull drivers from the 2 registry keys. (Just import from autoruns powershell github)
| Get-ProcessNamedPipes | FALSE |  |  |  | Windows often perform IPC (inter-process communication) using named pipes https://github.com/mgreen27/Powershell-IR/blob/master/Content/Process/Get-SimpleNamedPipe.ps1
| Get-PSServices | FALSE |  |  |  | Powershell version of get-services: https://github.com/mgreen27/Powershell-IR/blob/master/Content/ASEP/Get-PSIService.ps1
| Get-PSDrivers | FALSE |  |  |  | Powershell version of get-drivers https://github.com/mgreen27/Powershell-IR/blob/master/Content/ASEP/Get-Drivers.ps1
| Get-Atoms | FALSE |  |  |  | Shares Strings between processes. Atom tables are extremely interesting from a forensic perspective, because many Windows API functions create atoms without explicitly saying so. https://github.com/mgreen27/Powershell-IR/blob/master/Content/Process/Get-Atom.ps1
| Get-ProcessTokens | FALSE
| Get-ProcDump | FALSE
Exec_Historical
| Get-SRUM | TRUE | Partial (2.0) |  |  | Records 30 to 60 days of historical system performance. Applications run, user account responsible for each, and application and bytes sent/received per application per hour. -SANS
| Get-PrefetchFiles | TRUE | Partial (2.0) |  |  | Kansa Cache Manager monitors all files and directories referenced for each application or process and maps them into a .pf file.
| Get-PrefetchListing | TRUE | Partial (2.0) |  |  | Kansa. Prefetch files contain the name of the executable, a Unicode list of DLLs used by that executable, a count of how many times the executable has been run, and a timestamp indicating the last time the program was run. -forensics wiki
| Get-AppCompactCache | TRUE PARSER | FALSE |  |  | Kansa. AKA shimcache Tracks the executables file name, file size, last modified time, and in Windows XP the last update time - SANS
| Get-Amcache | PARSER | FALSE |  |  | -records the recent processes that were run and lists the path of the files Get-RawFile
| Get-JumpList | FALSE |  |  |  | - Windows 7 task bar (Jump List) is engineered to allow users to “jump” or access items they have frequently or recently used quickly and easily -SANS
| Get-CCM_RecentlyUsedApps | FALSE |  |  |  | Kansa sccm interations recording file execution (?) not sure
| Get-LastMRU | FALSE |  |  |  | Tracks the specific executable used by an application to open the files documented in the OpenSaveMRU key.
| Get-RecentApps | FALSE |  |  |  | GUI Program execution launched on the Win10 system is tracked in the RecentApps key -SANS
| Get-UserAssist | FALSE |  |  |  | GUI-based programs launched from the desktop are tracked in the launcher on a Windows System. - SANS
| Get-BAM | FALSE |  |  |  | Windows Background Activity Moderator (BAM) -SANS https://github.com/mgreen27/Powershell-IR/blob/master/Content/Other/Get-BAMParser.ps1
Exec_Triggers
| Get-Autorunsc | TRUE | Partial (2.0) |  | -probably should be broken into respective autorun categories to allow better fidelity in comparisons
| Get-WMIevtConsumer | FALSE |  |  | Check if autoruns does this | https://github.com/mgreen27/Powershell-IR/blob/master/Content/ASEP/Get-WMIEventConsumers.ps1
| Get-WMIevtFilter | FALSE |  |  | Check if autoruns does this | https://github.com/mgreen27/Powershell-IR/blob/master/Content/ASEP/Get-WMIEventFilters.ps1
| Get-WMIFltConBin | FALSE |  |  | Check if autoruns does this | https://github.com/mgreen27/Powershell-IR/blob/master/Content/ASEP/Get-WMIEventBindings.ps1
| Get-ServicesTrigs | FALSE |  |  |  | Persistence thru triggers https://github.com/mgreen27/Powershell-IR/blob/master/Content/ASEP/Get-Service_Trig.ps1
| Get-ServicesFails | FALSE |  |  |  | Persistence thru service failure recovery actions https://github.com/mgreen27/Powershell-IR/blob/master/Content/ASEP/Get-Services_Fail.ps1
| Get-IFEO | FALSE |  |  |  | Autorun by attaching a debugger https://github.com/mgreen27/Powershell-IR/blob/master/Content/ASEP/Get-IFEO.ps1
| Get-PsProfile | FALSE |  |  |  | Autoruns by powershell profile modifications https://github.com/mgreen27/Powershell-IR/blob/master/Content/ASEP/Get-PSProfiles.ps1
| Get-PSAutoRun | FALSE |  |  |  | Powershell version of autorun https://github.com/mgreen27/Powershell-IR/blob/master/Content/05Get-PSAutorun.ps1 -Also External
| Get-SchedTasks | FALSE |  |  |  | Included inside of Autoruns. But have a breakout function
Disk
| Get-DirectoryListings | TRUE | Partial (2.0) |  | -Add User Recycle bin -Add User Temp - Takes a lot of RAM for full listings
| Get-DiskInfo | TRUE | Partial (2.0) |  | Add Disk Partitions
| Get-FileOrFolder | TRUE | Partial (2.0) |  | -Merge Large File | Get Event Logs: Application// Security// System// Windows PowerShell// PowerShell%4Operational// SmbClient%4Security// Security%4Firewall// Sysmon%4Operational// AppLocker%4EXE and DLL// AppLocker%4MSI and Script // AppLocker%4Packaged app-Execution// AppLocker%4Packaged app-Deployment// DeviceGuard%4Operational// Defender%4Operational// RemoteConnectionManager%4Operational //WLAN Operational //WMI Activity //WinRM
| Get-RawFile | TRUE | Partial (2.0) |  |  | Get Registry: SOFTWARE \\ SECURITY \\ SYSTEM
| Get-VSSFileOrFOlder | TRUE | False |  | Add wildcard Support | Get oldest evtx: Security\\ System\\ Application
| Get-VSSCopiesInfo | TRUE | FALSE |  |  | https://github.com/zloeber/Powershell/blob/master/OS/Multiple%20Runspace/Get-RemoteShadowCopyInformation.ps1
| Get-VSSVolumesInfo | TRUE | FALSE |  |  | https://github.com/zloeber/Powershell/blob/master/OS/Multiple%20Runspace/Get-RemoteShadowCopyInformation.ps1
| Get-VSSDirList | FALSE
| Get-MasterFileTable | FALSE
| Get-USNJournal | FALSE
| Get-MBR | FALSE |  |  |  | Master boot record https://github.com/mgreen27/Powershell-IR/blob/master/Content/Disk/Get-MasterBootRecord.ps1
| Get-VBR | FALSE |  |  |  | volume boot record
| Get-RegistryKey | FALSE |  |  |  | https://github.com/zloeber/Powershell/blob/master/OS/Multiple%20Runspace/Get-RemoteRegistry.ps1
| Get-FileHashes | FALSE
| Get-FileEntropy | FALSE |  |  |  | https://github.com/Infocyte/PSHunt/blob/master/Surveys/Survey.ps1
| Check-DiskEncryption | FALSE
| Get-FileDACLs | FALSE
Memory
| Capture-Memory | TRUE | Partial (2.0) | -Dumsp RAM to disk before export | Figure out kerberos restricted delegation? -Redirect ram cap I/O to PS session
| Get-Pagefile | FALSE
| Get-hiberfil | FALSE
| Get-minidumps | FALSE
| Get-appdumpes | FALSE
Misc
| Check-Privs | TRUE | Partial (2.0)
| Get-Nothing | TRUE | Partial (2.0)
| Get-USBHistory | FALSE
| Get-InstalledPrinters | FALSE |  |  |  | https://github.com/zloeber/Powershell/blob/master/OS/Multiple%20Runspace/Get-RemoteInstalledPrinters.ps1
| Get-PlugNPlay | FALSE
| Check-ComputerIsVirtual | FALSE |  |  |  | https://github.com/zloeber/Powershell/blob/master/OS/Linear/Get-ComputerVirtualStatus.ps1
| Search-System32NotHardLinks | FALSE |  |  |  | Looks for binaries in system32 that are not hardlinks to SxS https://github.com/mgreen27/Powershell-IR/blob/master/Content/Disk/Get-System32NotHardLinks.ps1
| Search-Yara | FALSE |  |  |  | https://github.com/davehull/Kansa/blob/master/Modules/IOC/Get-Loki.ps1
| Get-BitsParser | FALSE |  |  |  | Reads BITS jobs from the que https://github.com/mgreen27/Powershell-IR/blob/master/Content/Other/Get-BitsParser.ps1
| Search-ZoneID | FALSE
| Search-AltDataStream | FALSE
| Search-InjectedThreads | FALSE |  |  |  | Kansa https://github.com/mgreen27/Powershell-IR/blob/master/Content/02Get-InjectedThread.ps1
| Signature-Check | FALSE |  |  |  | Check if a file's signature is valid
Network
| Get-ARPCache | TRUE | Partial (2.0)
| Get-DNSCache | TRUE | Partial (2.0)
| Get-Interfaces | TRUE | Partial (2.0)
| Get-MappedDrives | TRUE | Partial (2.0)
| Get-NetworkShares | TRUE | Partial (2.0)
| Get-FirewallRules | FALSE |  |  |  | https://github.com/zloeber/Powershell/blob/master/OS/Linear/Get-RemoteFirewallRulesV1.ps1
| Get-RoutingTable | FALSE |  |  |  | https://github.com/zloeber/Powershell/blob/master/OS/Multiple%20Runspace/Get-RemoteRouteTable.ps1
| Get-NetSharesSessionInfo | FALSE |  |  |  | Win32_ServerConnection https://github.com/zloeber/Powershell/blob/master/OS/Multiple%20Runspace/Get-RemoteShareSessionInfomation.ps1
| Get-NetSharesPermissions | FALSE |  |  |  | https://github.com/mgreen27/Powershell-IR/blob/master/Content/Configuration/Get-SharePermissions.ps1
| Get-PreviousNetworks | FALSE |  |  |  | netstat -r SOFTWARE\Microsoft\Windows NT\CurrentVersion\NetworkList
| Get-WLANHistory | FALSE
| Get-WorkstationADInfo | FALSE
| Get-AppliedlGPOs | FALSE |  |  |  | https://github.com/zloeber/Powershell/blob/master/OS/Multiple%20Runspace/Get-RemoteAppliedGPOs.ps1
| Get-GPResultant | FALSE
| Get-Certs | FALSE |  |  |  | Kansa
| Get-PortProxies | FALSE
System
| Get-ENVVar | TRUE | Partial (2.0)
| Get-GeneralInfo | TRUE | Partial (2.0) |  | -Date/Timezone/Time -Serial Number -OS version(?) | Compare agaisnt https://github.com/mgreen27/Powershell-IR/blob/master/Content/Configuration/Get-SystemInfo.ps1
| Get-HotFixes | TRUE | Partial (2.0)
| Get-InstalledSoftware | TRUE | Partial (2.0)
| Get-Logs-ntuser | TRUE | Partial (2.0) |  | Convert to VSS method
| Get-Logs-UsrClass | TRUE | Partial (2.0) |  | Convert to VSS method
| Get-ServerFeatures | FALSE |  |  |  | Win32_ServerFeature Win32_OptionalFeature https://github.com/zloeber/Powershell/blob/master/OS/Multiple%20Runspace/Get-RemoteShareSessionInfomation.ps1
| Get-AMHealth | FALSE |  |  |  | Get's anti malware status https://github.com/mgreen27/Powershell-IR/blob/master/Content/Configuration/Get-AMHealthStatus.ps1
| Get-RegistryKey | FALSE |  | Command of Get-RawFile
| Get-WinEvtx | FALSE |  | Command of Get-File
User
| Get-LocalAccounts | TRUE | Partial (2.0) |  | Last PW Change
| Get-LocalGroups | TRUE | Partial (2.0)
| Get-LoggedOnAccounts | TRUE | Partial (2.0)
| Get-LoggedOnUsers | TRUE | Partial (2.0)
| Get-RDPUsage | FALSE |  |  |  | Remote desktop destinations are tracked per-user NTUSER\Software\Microsoft\Terminal Server Client\Server https://github.com/mgreen27/Powershell-IR/blob/master/Content/Logs/Get-RDPConnections.ps1
| Get-Shellbags | FALSE
| Get-RecentsFolders | FALSE
| Get-RecentDocs | FALSE
| Get-RecentShortcuts | FALSE
| Get-PSCommandHistory | FALSE |  |  |  | Command history (PS5+) C:\USERS\<USERNAME>\AppData\Roaming\Microsoft\Windows\PowerShell\PSReadline\ConsoleHost_history.txt
| Get-KerberosTicketCache | FALSE |  |  |  | klist.exe
| Get-KerberosTGTs | FALSE |  |  |  | https://github.com/spohara79/TGT---Golden-Silver-Ticket/blob/master/HuntGoldenTicket.ps1
| Get-KerberosTGSs | FALSE |  |  |  | https://gist.github.com/jaredcatkinson/c95fd1e4e76a4b9b966861f64782f5a9
| Get-TempDirListings | FALSE |  |  |  | Get's the directory listing for each user
| Get-StoredCredList | FALSE |  |  | cmdkey /list | Enum Cert Store https://github.com/mgreen27/Powershell-IR/blob/master/Content/Configuration/Get-CertStore.ps1
| Get-RecycleBins | FALSE |  |  |  | SANS Windows DFIR Poster
| Get-WinSearch | FALSE |  |  |  | SANS Windows DFIR Poster Keywords searched for from the START menu bar on a Windows 7 machine.
| Get-FileExplorerPaths | FALSE
| Get-FileSavesDiag | FALSE
| Get-LocalAdmins | FALSE
| Get-LogOpenSavePIDMRU | FALSE |  |  |  | https://github.com/davehull/Kansa/blob/master/Modules/Log/Get-LogOpenSavePidlMRU.ps1
| Get-RunCommands | FALSE
| Get-ThumbsCache | FALSE |  |  |  | SANS Windows DFIR Poster

## Parsers
SubSection | Parser | Required Collector | Developed | Tested (2008R2-2016) | Issues | Proposed Mods
Apps
| Parse-OfficeMRU |  | FALSE |  |  | https://github.com/davehull/Kansa/blob/master/Modules/Log/Get-OfficeMRU.ps1
Exec_Historical | Parse-PrefetchTimeline | Get-PrefetchFiles | TRUE | Partial (2.0)
Disk
| Parse-MFT | Get-MSFT | FALSE |  |  | Parse MSFT into csv format.
Memory
Parse-Processes
Misc
| Send-ToSplunk |  | TRUE | Partial (3.0+)
Upload-Kibana
Network
Exec_Historical
| Parse-AppCompatCacheParser | Get-RawFile | TRUE
| Parse-Amcache | Get-RawFile | TRUE
| Parse-Memory-Processes | Get-Memory | FALSE
| Parse-SRUMCache |  | FALSE
| Parse-Prefetch | Get-RawFile $Registry_HKLM | FALSE
| Parse-ImagePathExecutionOptions |  | FALSE |  |  | Kansa
System
| Parse-EvtxToJson | Get-File "$Path" | FALSE |  |  | Parse EVTX to json with full events. (I have a close solution)
User
| Parse-RecentDocs | Get-ntuser.ps1 | False-Kansa |  |  | Extract Recent Docs key to csv.
| Parse-OpenSavePidlMRU | Get-File "$Path" | False-Kansa |  |  | https://github.com/davehull/Kansa/blob/master/Modules/Log/Get-LogOpenSavePidlMRU.ps1
| Parse-UserAssist | Get-File "$Reg" | False-Kansa |  |  | https://github.com/davehull/Kansa/blob/master/Modules/Log/Get-LogUserAssist.ps1

## Comparisons
Scripts
|  | Light |  |  | Heavy
|  | Jyn | Get-Baseline | ? | POSH-R2 | ACE | Powershell Forensics | Kansa | PSHunt | Powershell IR | YACK | 3rd Party | Log Collector | Biggie | ir-rescue
Overall Requirements
Win7+
Remote
Correct Data
Formats Data
Collected Data
Apps
HBSS-Events
HBSS-HIPShield
IIS-AccessLogs
IIS-DirListing
IIS-WebsitesInfo
IIS-ErrorLogs
FirewallLogs
OfficeRecentFiles
OutlookAttachments
IEFileInteractions
(?) BrowserCache
BrowserArtifacts
BrowserDownloadHistory
BrowserCookies
BrowserHistory
SkypeHistory
Exec_Current
Processes
ProcessSockets
ProcessHandles
ProcessModules
Services
Drivers
ProcessNamedPipes
Atoms
ProcessTokens
ProcDump
Exec_Historical
SRUM
PrefetchFiles
PrefetchListing
AppCompactCache
Amcache
CCM_RecentlyUsedApps
JumpList
LastMRU
RecentApps
UserAssist
BAM
Exec_Triggers
Autorunsc
WMIevtConsumer
WMIevtFilter
WMIFltConBin
ServicesTrigs
ServicesFails
IFEO
PsProfile
PSAutoRun
Disk
DirectoryListings
DiskInfo
FileOrFolder
RawFile
VSSFile
VSSCopiesInfo
VSSVolumesInfo
VSSDirList
MasterFileTable
USNJournal
MBR
VBR
FileHashes
FileEntropy
Check-DiskEncryption
FileDACLs
Memory
Capture-Memory
Pagefile
hiberfil
minidumps
appdumpes
Memory-Artifacts
Misc
Check-Privs
Nothing
USBHistory
InstalledPrinters
PlugNPlay
Check-ComputerIsVirtual
Search-System32NotHardLinks
Search-Yara
BitsParser
Search-ZoneID
Search-AltDataStream
Search-InjectedThreads
Sig-Check
Network
ARPCache
DNSCache
Interfaces
MappedDrives
NetworkShares
FirewallRules
RoutingTable
NetSharesSessionInfo
NetSharesPermissions
PreviousNetworks
WLANHistory
WorkstationADInfo
AppliedlGPOs
GPResultant
Certs
PortProxies
System
ENVVar
GeneralInfo
HotFixes
InstalledSoftware
Logs-ntuser
Logs-UsrClass
ServerFeatures
AMHealth
RegistryKey
WinEvtx
User
LocalAccounts
LocalGroups
LoggedOnAccounts
LoggedOnUsers
RDPUsage
Shellbags
RecentsFolders
RecentDocs
RecentShortcuts
PSCommandHistory
KerberosTicketCache
KerberosTGTs
KerberosTGSs
TempDirListings
StoredCredList
RecycleBins
WinSearch
FileExplorerPaths
FileSavesDiag
LocalAdmins
LogOpenSavePIDMRU
RunCommands
ThumbsCache
UserAssist
Additional Features
Timeline Creation
Forensically Sound

## Notes
Notes
win7 oddities
powershell.exe -v 2 .\yack.ps1
List .net assemblies:
[System.IO.Compression.GZipStream].GetMethods() | sort name | ft name
===
$null = New-Item -Path "$CollectLogPath" -Force -ItemType "file"
====
$MyBuffer = New-Object Byte[] $NextChunkSize
====
$Dependencies = @()
$Dependencies.Contains($Dep)
-> $($Dependencies -contains $Dep)
====
foreach (doesn't check for $null)
===
#Doesnt list all names
$CollectorResult.PSobject.Properties.name -match "OutputType"
-> Get-Member -inputobject $CollectorResult -name "OutputType"
====
#Objects returned by return statement, get wrapped into PSObject in V2:
#return System.Management.Automation.PSObject in V2 and System.String in V4.
$CollectorResult.Content = $ParsedEvents | Select-Object $properties
$CollectorResult.Content = $ParsedEvents | Select-Object ([String[]]$properties)
====
command line doesn't like commands after the run cmd (&)... they get eaten
======
Something is bugging out on ($MyBuffer = New-Object Byte[] $File.Length) while debugging
Get-RawFile is currently not working... It's because of GetBase64GzippedStream and the byte[].
This is probably broken elsewhere
$destBytes = [System.Byte[]]::CreateInstance([System.Byte],$TransferLength)
===
$MyArray = @(1, 2, 3, 4, 5, 6, 7)
return $MyArray #This returns individual bytes
return ,$MyArray #This returns the byte array
AND
return $MemStrm.ToArray()
return ,$MemStrm.ToArray()
====
[System.IO.Compression.GZipStream] doesn't contain a method named 'CopyTo'.
Custom Loop
====
Working on...
I changed the file transfer to a seperate folder. It's not working atm.
Include files doesnt work remote... start large amount of functions...